# DATA_SCOUT — MVP Implementation Plan

Version: 1.0 | Last Updated: 2026-02-21
Sprint Duration: 4 Weeks (Feb 24 — Mar 23, 2026)
Team Size: 5 Engineers
Goal: Ship a working end-to-end flow: Upload → Clean → Train → Chat → Report

## Team Roster

| # | Role | Name Alias | Primary Responsibility | Secondary Responsibility |
| --- | --- | --- | --- | --- |
| 🔵 P1 | Backend Engineer | Backend Lead | Data & ML pipelines, Celery workers, business logic | Database models, service layer |
| 🟢 P2 | Frontend Engineer | Frontend Lead | React SPA, component library, state management, UX | API integration, WebSocket client |
| 🟡 P3 | API & Integration Engineer | API Lead | FastAPI routers, Pydantic schemas, auth, WebSocket server | LLM integration, RAG chatbot |
| 🟠 P4 | DevOps Engineer | DevOps Lead | Docker, CI/CD, database setup, infra, monitoring | Security hardening, deployment |
| 🟣 P5 | QA & Documentation Engineer | QA Lead | Test suites, load testing, documentation, validation | Data fixtures, integration tests |

## Sprint Overview

Week 1: Foundation          Week 2: Core Pipelines       Week 3: Intelligence        Week 4: Polish & Ship
(Feb 24 — Feb 28)           (Mar 3 — Mar 7)              (Mar 10 — Mar 14)           (Mar 17 — Mar 21)
                                                                                      + Buffer (Mar 22-23)
│                           │                             │                            │
├─ Project scaffolding      ├─ Data cleaning pipeline     ├─ RAG chatbot (FAISS+LLM)  ├─ Integration testing
├─ Docker environment       ├─ AutoML training pipeline   ├─ Report generation engine  ├─ Bug fixes
├─ DB models & migrations   ├─ Upload + Preview UI        ├─ Chat UI                  ├─ Performance tuning
├─ Auth system              ├─ Data cleaning UI           ├─ Results dashboard UI     ├─ Documentation final
├─ Component library        ├─ Training endpoints         ├─ Explainability (SHAP)    ├─ Demo preparation
└─ CI pipeline              └─ WebSocket progress         └─ Report UI               └─ MVP release

## Week 1: Foundation (Feb 24 — Feb 28)

Goal: Every team member has a working local environment. Backend skeleton, database, auth, Docker, CI, and base React app are all functional.

### 🔵 P1 — Backend Engineer

| Day | Task | Deliverables | Dependencies | Definition of Done |
| --- | --- | --- | --- | --- |
| Mon | Set up backend project structure | backend/app/ skeleton: main.py, core/, models/, schemas/, services/, pipelines/, workers/ folders with __init__.py | None | uvicorn app.main:app starts without error |
| Mon | Configure settings with pydantic-settings | core/config.py with DATABASE_URL, REDIS_URL, MINIO_ENDPOINT, JWT_SECRET, all LLM API keys | .env.example from P4 | Settings load from .env; missing vars raise clear error |
| Tue | Create SQLAlchemy ORM models | models/user.py, dataset.py, job.py, model_result.py, conversation.py, report.py with relationships | PostgreSQL running (P4) | All models importable; relationships defined |
| Tue | Set up Alembic migrations | alembic/ directory, env.py configured for async | DB models | alembic upgrade head creates all tables |
| Wed | Implement database session management | db/session.py — async session factory, get_db dependency | DB running | Dependency injection works in test route |
| Wed | Build AuthService | services/auth_service.py — register, login, hash password (bcrypt), generate/verify JWT | models, session | Register → Login → get access token works |
| Thu | Build data ingestion pipeline (Phase 1) | pipelines/ingestion.py — parse CSV/XLSX, chunked reading, metadata extraction | pandas, openpyxl | Correctly parses 5 test files of varying formats |
| Thu | Build column type detection | pipelines/type_detection.py — multi-heuristic detection (numeric, categorical, datetime, boolean, identifier) | ingestion.py | ≥95% accuracy on test fixtures |
| Fri | Set up Celery app + Redis broker | core/celery_app.py — Celery instance, queue config, result backend | Redis running (P4) | Basic task submits and completes; result retrievable |
| Fri | Write data cleaning task skeleton | workers/data_tasks.py — clean_dataset_task with progress updates via self.update_state() | Celery app | Task submittable; progress states visible in Redis |

Blockers to Watch: - Needs P4 to have PostgreSQL + Redis running by Tuesday morning - Coordinate with P3 on Pydantic schema shapes for auth endpoints

Key Decisions: - Use asyncpg driver for async PostgreSQL - bcrypt cost factor = 12 - JWT algorithm = HS256, access TTL = 30 min, refresh TTL = 7 days

### 🟢 P2 — Frontend Engineer

| Day | Task | Deliverables | Dependencies | Definition of Done |
| --- | --- | --- | --- | --- |
| Mon | Initialize React + Vite project | frontend/ with Vite 5, React 18, folder structure (components/, pages/, hooks/, services/, store/, styles/) | None | npm run dev serves blank app at localhost:3000 |
| Mon | Set up design system: CSS variables + globals | styles/variables.css (all tokens from FRONTEND_DESIGN.md), styles/globals.css (reset, base typography), styles/animations.css | None | All tokens importable; dark theme toggle-ready |
| Mon | Set up ESLint + Prettier | .eslintrc.cjs, .prettierrc | None | npm run lint passes on initial codebase |
| Tue | Build atomic UI components (Batch 1) | Button.jsx, Input.jsx, Card.jsx, Badge.jsx, Spinner.jsx + CSS Modules | Design tokens | Components render correctly with all variants |
| Tue | Build atomic UI components (Batch 2) | Modal.jsx, Toast.jsx, ProgressBar.jsx, Skeleton.jsx, Tabs.jsx, Toggle.jsx, Dropdown.jsx, Tooltip.jsx | Design tokens | All components render + keyboard accessible |
| Wed | Build layout components | Header.jsx (logo, nav links, user menu), Sidebar.jsx (collapsible), PageContainer.jsx, Footer.jsx, ProtectedLayout.jsx | UI components | App has visible working layout at all breakpoints |
| Wed | Set up React Router | App.jsx with all routes defined; ProtectedLayout wraps authenticated routes | Layout components | Navigation between pages works; unauthenticated redirects to /login |
| Thu | Build auth pages | LoginPage.jsx, RegisterPage.jsx with form validation (React Hook Form + Zod) | UI components, router | Forms validate input; submit button triggers API call (mock for now) |
| Thu | Set up Zustand stores | useAuthStore.js (tokens, user, login/logout), useToastStore.js (global notifications), useDatasetStore.js, useJobStore.js | None | Stores work in isolation; auth state persists in localStorage |
| Fri | Build Axios API client + interceptors | services/api.js — base URL, auth header injection, 401 auto-refresh, error handling | useAuthStore | API calls include token; 401 triggers refresh flow |
| Fri | Build HomePage.jsx (Landing) | Hero section, “How it Works” 4-step section, feature cards, footer | UI components, layout | Visually polished landing page; responsive |

Blockers to Watch: - Coordinate with P3 on API response shapes for auth endpoints - Need design tokens finalized Day 1 (from FRONTEND_DESIGN.md — already done ✅)

Key Decisions: - Zustand over Redux (no boilerplate) - CSS Modules over Tailwind (full control, no extra dependency) - React Hook Form + Zod for form validation

### 🟡 P3 — API & Integration Engineer

| Day | Task | Deliverables | Dependencies | Definition of Done |
| --- | --- | --- | --- | --- |
| Mon | Set up FastAPI app factory | main.py — create_app(), CORS middleware, exception handlers, router mounting | None | GET /health returns {"status": "healthy"} |
| Mon | Define Pydantic schemas (auth) | schemas/auth.py — LoginRequest, RegisterRequest, TokenResponse, UserResponse | None | Schemas validate correct/incorrect payloads |
| Tue | Build auth router | routers/auth.py — POST /register, POST /login, POST /refresh | AuthService (P1) | Full auth flow works via Swagger docs |
| Tue | Build auth dependencies | dependencies.py — get_current_user, get_db, require_auth | Auth router, JWT | Protected endpoints reject invalid tokens |
| Wed | Define Pydantic schemas (upload, data) | schemas/upload.py — UploadResponse, DatasetInfo; schemas/data.py — PreviewResponse, CleanRequest, QualityReport; schemas/common.py — ErrorResponse, JobStatus | Coordinate with P1 on models | All schemas documented in Swagger |
| Wed | Build upload router | routers/upload.py — POST /upload (multipart), GET /upload/{id}, DELETE /upload/{id} | Pydantic schemas, MinIO (P4) | File uploads to MinIO; metadata stored in DB |
| Thu | Build data router | routers/data.py — GET /data/{id}/preview, POST /data/{id}/clean, GET /data/{id}/quality | Data schemas, cleaning task (P1) | Preview returns first 20 rows; clean dispatches Celery task |
| Thu | Build job status router | routers/jobs.py — GET /jobs/{id}, DELETE /jobs/{id} | Job model (P1) | Job status polling works; cancel revokes Celery task |
| Fri | Build WebSocket endpoint for job progress | websocket/job_progress.py — /ws/jobs/{job_id} | Celery progress events | Client receives real-time progress updates |
| Fri | End-to-end test: upload → clean → quality | Manual test through Swagger | All above | Full flow works from API; documented |

Blockers to Watch: - P1 must deliver AuthService by Tuesday EOD - P4 must have MinIO running by Wednesday morning - Coordinate schema shapes with P2 for frontend integration

Key Decisions: - All async endpoints (async def) - Consistent error format: {"error": {"code": "...", "message": "...", "details": {...}}} - API versioning: /api/v1/ prefix on all routes - Rate limiting: handled by Nginx (P4), not application-level for MVP

### 🟠 P4 — DevOps Engineer

| Day | Task | Deliverables | Dependencies | Definition of Done |
| --- | --- | --- | --- | --- |
| Mon | Create repository structure | Root data_scout/ with frontend/, backend/, nginx/, scripts/, DOCS/, .github/, .env.example, .gitignore, Makefile | None | git init + initial commit with structure |
| Mon | Write docker-compose.yml (dev) | Services: postgres, redis, minio with health checks, volumes, ports | None | docker compose up starts all 3 services; health checks pass |
| Tue | Write backend Dockerfile | Multi-stage: Python 3.11-slim, install deps, copy app | requirements.txt (P1) | docker build succeeds; backend starts in container |
| Tue | Write frontend Dockerfile | Multi-stage: Node 20 build → Nginx serve | package.json (P2) | docker build succeeds; frontend serves from Nginx |
| Tue | Add backend + frontend to docker-compose | backend, celery-worker services with env vars, frontend service | Dockerfiles | docker compose up starts full stack |
| Wed | Write Nginx reverse proxy config | nginx/nginx.conf — / → frontend, /api/ → backend:8000, /ws/ → backend WebSocket, SSL placeholder, rate limiting, security headers | Docker Compose | Requests routed correctly through Nginx |
| Wed | Create MinIO bucket initialization script | scripts/init_minio.sh — create datasets, models, reports buckets on first run | MinIO running | Buckets exist after script runs |
| Thu | Set up GitHub Actions CI | .github/workflows/ci.yml — lint backend (ruff), test backend (pytest), lint frontend (eslint), test frontend (vitest), build Docker images | Tests exist (P5) | CI passes on push to main and develop |
| Thu | Write Makefile with common commands | Targets: dev, build, test, lint, migrate, seed, logs, clean | Docker Compose | make dev starts everything; make test runs all tests |
| Fri | Write docker-compose.dev.yml (overrides) | Hot-reload for backend (uvicorn –reload), frontend (vite dev server), exposed debug ports, no SSL | Base compose | docker compose -f docker-compose.yml -f docker-compose.dev.yml up enables hot-reload |
| Fri | Validate full local dev environment | Run full stack locally; verify all services connect; document any setup quirks | All above | New developer can make dev and have everything running in <5 minutes |

Blockers to Watch: - Needs requirements.txt from P1 by Tuesday morning - Needs package.json from P2 by Tuesday morning - CI depends on test files from P5

Key Decisions: - PostgreSQL 16, Redis 7, MinIO latest - Dev mode: volumes mount source code for hot-reload - .env.example includes all required vars with placeholder values - Makefile as single entry point for all commands

### 🟣 P5 — QA & Documentation Engineer

| Day | Task | Deliverables | Dependencies | Definition of Done |
| --- | --- | --- | --- | --- |
| Mon | Set up pytest infrastructure | backend/tests/conftest.py — async test client, test DB fixture (SQLite or test PostgreSQL), auth fixture, temp file fixtures | P1 project structure | pytest runs with 0 tests collected (no errors) |
| Mon | Create test data fixtures | tests/fixtures/sample_clean.csv, sample_messy.csv (nulls, outliers, duplicates, mixed types), sample_imbalanced.csv | None | 4 fixture files with realistic data; documented column descriptions |
| Tue | Write unit tests: type detection | tests/unit/test_type_detection.py — numeric, categorical, datetime, boolean, identifier, mixed-type columns | type_detection.py (P1) | ≥10 test cases; all pass |
| Tue | Write unit tests: auth service | tests/unit/test_auth.py — register, login, JWT validity, expired token, wrong password | auth_service.py (P1) | ≥8 test cases; all pass |
| Wed | Write unit tests: Pydantic schemas | tests/unit/test_schemas.py — valid/invalid payloads for all schemas | Schemas (P3) | ≥15 test cases covering edge cases |
| Wed | Set up Vitest for frontend | frontend/vitest.config.js, sample component test | P2 project structure | npm test runs without error |
| Thu | Write frontend component tests | Button.test.jsx, FileDropzone.test.jsx, DataTable.test.jsx — render, interaction, accessibility | Components (P2) | ≥10 test cases; all pass |
| Thu | Write integration test: auth flow | tests/integration/test_auth_flow.py — register → login → access protected → refresh → invalid token | Auth system (P1+P3) | Full flow passes end-to-end |
| Fri | Update README.md | Getting started, prerequisites, installation, dev workflow, project structure overview, contributing guide | All above | New developer can set up in <10 minutes following README |
| Fri | Review & validate all documentation | Cross-check DOCS/ folder against actual implementation; flag any discrepancies; add missing details | All DOCS/ files | All docs reflect actual state of codebase |

Blockers to Watch: - Test writing depends on P1/P3 delivering implementations - If implementations are delayed, write tests against planned interfaces (TDD approach)

Key Decisions: - pytest + pytest-asyncio + httpx for backend tests - Vitest + React Testing Library for frontend tests - Test fixtures committed to repo (small, synthetic data) - Coverage target: ≥70% for MVP (stretch: 80%)

## Week 2: Core Pipelines (Mar 3 — Mar 7)

Goal: Data cleaning and ML training pipelines work end-to-end. Frontend shows upload, data preview, cleaning, and training progress.

### 🔵 P1 — Backend Engineer

| Day | Task | Deliverables | Depends On | Done When |
| --- | --- | --- | --- | --- |
| Mon | Build missing value imputation | pipelines/cleaning.py — strategy matrix: mean/median/mode/drop per column type + missingness % | type_detection.py | Correct imputation on sample_messy.csv; 0 nulls remaining |
| Mon | Build outlier detection + treatment | pipelines/cleaning.py — IQR method (default), Z-score (optional); cap/remove/flag modes | Cleaning module | Outliers detected and treated; counts match manual check |
| Tue | Build deduplication + type correction | pipelines/cleaning.py — remove exact dupes; coerce string-numbers/dates | Cleaning module | Duplicates removed; type corrections logged |
| Tue | Build feature engineering | pipelines/feature_engineering.py — datetime features, frequency encoding, interaction terms, variance filter, correlation filter | Cleaning output | Generated features pass validation; no constant/duplicate features |
| Wed | Build data validation (pre+post) | pipelines/validation.py — pre-checks (min rows/cols, encoding), post-checks (no nulls, no dupes, row loss <30%), quality score | All cleaning steps | Quality score computed correctly for test datasets |
| Wed | Build full DataService orchestration | services/data_service.py — orchestrate: ingest → validate → clean → feature_eng → validate → store cleaned | All pipeline modules | DataService.process(dataset_id) returns quality report |
| Thu | Build task detection | pipelines/task_detection.py — classification/regression/clustering detection with confidence score | Cleaned data | ≥95% correct on 10+ test datasets |
| Thu | Build AutoML training pipeline | pipelines/model_training.py — FLAML wrapper, model pool filtering by dataset size, time budget enforcement | Task detection | FLAML trains and returns results within time budget |
| Fri | Build evaluation pipeline | pipelines/evaluation.py — metrics per task type, overfitting detection, cross-validation | Model training | Metrics computed; overfitting flag works |
| Fri | Build model recommendation engine | services/ml_service.py — rank models, generate justification text, extract feature importance | Evaluation | Recommendation includes: model name, justification, top-3 features |

End of Week Milestone: MLService.train_and_evaluate(dataset_id, target_col) runs end-to-end and returns ranked models with recommendation.

### 🟢 P2 — Frontend Engineer

| Day | Task | Deliverables | Depends On | Done When |
| --- | --- | --- | --- | --- |
| Mon | Build FileDropzone component | Upload/FileDropzone.jsx — drag-and-drop, file validation (type + size), visual feedback | UI components | Accepts valid files; rejects invalid ones with error |
| Mon | Build UploadProgress component | Upload/UploadProgress.jsx — per-file progress bar, cancel button | ProgressBar component | Shows real upload progress |
| Tue | Build UploadPage.jsx | Full upload page with dropzone + recent uploads table | FileDropzone, UploadProgress | File uploads work; recent files listed |
| Tue | Integrate upload with API | services/uploadService.js — POST /upload with FormData; useUpload.js hook | Upload API (P3) | Files upload to backend; response shown |
| Wed | Build DataTable component | DataPreview/DataTable.jsx — sorting, pagination, column type badges, alternating rows | UI components | 50K rows renders smoothly with pagination |
| Wed | Build QualityPanel component | DataPreview/QualityPanel.jsx — quality score meter, null/outlier/duplicate counts | Card, Badge | Shows all quality metrics |
| Thu | Build DataPage.jsx | Preview tab (DataTable) + Quality panel + Clean button + Before/After toggle | DataTable, QualityPanel | Full data preview + cleaning trigger works |
| Thu | Build CleaningActionLog component | DataPreview/CleaningActionLog.jsx — list of actions with affected rows, icons | Card component | Displays cleaning actions after clean completes |
| Fri | Build TrainingProgress component | MLDashboard/TrainingProgress.jsx — animated progress bar, model list with status icons, ETA | ProgressBar, WebSocket | Real-time progress updates from WebSocket |
| Fri | Build useWebSocket hook + useJobPolling | hooks/useWebSocket.js (auto-reconnect), hooks/useJobPolling.js (WS + HTTP fallback) | WebSocket endpoint (P3) | Progress updates received in real-time |

End of Week Milestone: User can upload a file → see preview → trigger cleaning → see before/after → start training → see live progress.

### 🟡 P3 — API & Integration Engineer

| Day | Task | Deliverables | Depends On | Done When |
| --- | --- | --- | --- | --- |
| Mon | Build ML schemas | schemas/ml.py — TrainRequest, TrainStatus, MLResults, ModelMetrics, Recommendation, FeatureImportance | Coordinate with P1 | Schemas match ML pipeline output |
| Mon | Build ML router | routers/ml.py — POST /ml/train, GET /ml/status/{job_id}, GET /ml/results/{dataset_id}, GET /ml/download/{dataset_id}/{model} | ML schemas, ML task (P1) | Training dispatches task; results retrievable |
| Tue | Build ML training Celery task | workers/ml_tasks.py — train_models_task with progress updates at each model | MLService (P1), Celery | Task reports progress; stores results |
| Tue | Build data cleaning Celery task (full) | workers/data_tasks.py — clean_dataset_task calling DataService, progress at each step | DataService (P1), Celery | Full cleaning runs async with progress |
| Wed | Enhance WebSocket with proper error handling | Error messages, reconnection guidance, auth check on WS connect | WS endpoint | Client gets clear errors on failure |
| Wed | Build file storage abstraction | services/storage_service.py — upload/download/delete files to MinIO; presigned download URLs | MinIO (P4) | Files stored and retrievable; URLs work |
| Thu | End-to-end API test: upload → clean → train → results | Full flow through Swagger / httpx | All endpoints | Screenshot/recording of full flow |
| Thu | Performance tune: pagination, query optimization | Add pagination to list endpoints; optimize DB queries with .options(selectinload) | All routers | List endpoints respond <200ms for 100 items |
| Fri | Write API documentation (OpenAPI enrichment) | Add descriptions, examples, tags to all endpoints; verify Swagger docs are complete | All routers | Swagger at /docs is fully documented and usable |
| Fri | Coordinate with P2 on frontend integration | Joint session: verify API shapes match frontend expectations; fix any mismatches | P2 frontend | No contract mismatches remaining |

End of Week Milestone: Full API surface (upload, data, ML, jobs) working and documented in Swagger.

### 🟠 P4 — DevOps Engineer

| Day | Task | Deliverables | Depends On | Done When |
| --- | --- | --- | --- | --- |
| Mon | Set up database backup script | scripts/backup_db.sh — pg_dump to timestamped file | PostgreSQL running | Backup file created; restore tested |
| Mon | Configure logging (structured JSON) | core/logging.py — structlog setup; middleware logs request_id, duration, status | Backend running | All requests logged in JSON format to stdout |
| Tue | Set up health check endpoint enhancement | routers/health.py — check DB, Redis, MinIO; return healthy / degraded | All services | /health accurately reflects service state |
| Tue | Add Alembic migration to CI | CI step: alembic upgrade head runs against test DB in CI | CI pipeline, migrations | CI fails if migration is broken |
| Wed | Configure Celery monitoring | Add Flower dashboard to docker-compose (dev); port 5555 | Celery running | Flower shows workers, queues, task history |
| Wed | Write seed script | scripts/seed_db.py — create test user, upload sample dataset, create initial data | Backend, DB | make seed creates usable test data |
| Thu | Optimize Docker images | Multi-stage builds; .dockerignore; layer caching; reduce image sizes | Dockerfiles | Backend image <500MB; Frontend image <50MB |
| Thu | Set up pre-commit hooks | .pre-commit-config.yaml — ruff (format + lint), eslint, prettier, trailing whitespace | None | pre-commit run --all-files passes |
| Fri | Write deployment script (staging) | scripts/deploy.sh — SSH to server, pull images, compose up, health check | Docker images | Script deploys to staging server (or local mimic) |
| Fri | Environment documentation | Document all env vars in .env.example with descriptions, defaults, and required/optional flags | All services | Every env var documented |

End of Week Milestone: Full Docker stack is optimized, monitored (Flower), seeded, and deployable.

### 🟣 P5 — QA & Documentation Engineer

| Day | Task | Deliverables | Depends On | Done When |
| --- | --- | --- | --- | --- |
| Mon | Write unit tests: cleaning pipeline | test_imputation.py, test_outliers.py — strategy matrix, edge cases (all-null, single-value, all-outlier) | cleaning.py (P1) | ≥15 test cases; all pass |
| Tue | Write unit tests: feature engineering | test_features.py — datetime extraction, frequency encoding, variance filter, correlation filter | feature_engineering.py | ≥10 test cases; all pass |
| Tue | Write unit tests: task detection | test_task_detection.py — binary, multiclass, regression, clustering, constant target, ID column | task_detection.py | ≥12 test cases; all pass |
| Wed | Write integration test: upload → clean → quality | test_cleaning_flow.py — upload messy file → trigger clean → poll job → verify quality report | Upload + data APIs | End-to-end flow passes |
| Wed | Write integration test: train → results | test_training_flow.py — upload → clean → train → poll → verify model results | ML APIs | End-to-end ML flow passes |
| Thu | Write frontend tests: UploadPage, DataPage | Test file selection, validation errors, API integration mocks, table rendering | Frontend pages (P2) | ≥8 test cases per page |
| Thu | Measure code coverage | Configure pytest-cov + Vitest coverage; generate reports | All tests | Backend ≥70%, Frontend ≥60% |
| Fri | Update test plan documentation | Update TEST_PLAN.md with actual test results, coverage numbers, known gaps | Test results | Test plan reflects ground truth |
| Fri | Manual QA: full user flow | Manually test upload → clean → train → results through UI; file bug reports | Running system | Bug list with severity (P0/P1/P2) created |

End of Week Milestone: ≥70% backend coverage; integration tests for both core pipelines; manual QA report.

## Week 3: Intelligence Layer (Mar 10 — Mar 14)

Goal: RAG chatbot, report generation, SHAP explainability, and all remaining UI pages are functional.

### 🔵 P1 — Backend Engineer

| Day | Task | Deliverables | Depends On | Done When |
| --- | --- | --- | --- | --- |
| Mon | Build row-to-text conversion | pipelines/ — convert dataframe rows to text chunks; generate statistical summary chunks; create schema description chunk | Cleaned data | Chunks are semantic and retrievable |
| Mon | Build FAISS indexing pipeline | services/rag_service.py — embed chunks with all-MiniLM-L6-v2, build FAISS FlatIP index, persist index | sentence-transformers, FAISS | Index built for test dataset; search returns relevant results |
| Tue | Build retrieval pipeline | services/rag_service.py — embed query, FAISS top-k search, quality gate (threshold=0.3), chunk filtering | FAISS index | Correct chunks retrieved for test questions |
| Tue | Build prompt construction | services/rag_service.py — system prompt + context chunks + conversation history + user question | Retrieval pipeline | Prompt fits within context window; grounding instructions present |
| Wed | Build post-response validation | services/rag_service.py — extract numerical claims, check against source chunks, compute grounding ratio | LLM response | Hallucinated claims detected; grounding ratio computed |
| Wed | Build SHAP explainability | pipelines/explainability.py — TreeExplainer/KernelExplainer, summary plot, feature importance plot, save as images | Trained models | SHAP plots generated and saved to storage |
| Thu | Build report generation engine | services/report_service.py — template-based report: summary, data quality, model comparison, feature importance, recommendations sections | All pipeline outputs | HTML report generated with real data + charts |
| Thu | Build report Celery task | workers/report_tasks.py — generate_report_task with section selection | ReportService | Async report generation works |
| Fri | Build model card generation | pipelines/explainability.py — structured model card: type, hyperparams, training shape, CV scores, overfitting report | ML pipeline | Model card JSON generated for every trained model |
| Fri | Performance optimization: caching | Add Redis caching for: dataset preview (5 min TTL), quality reports (until re-clean), embedding models (singleton) | Redis, all services | Repeated API calls are 10x faster |

### 🟢 P2 — Frontend Engineer

| Day | Task | Deliverables | Depends On | Done When |
| --- | --- | --- | --- | --- |
| Mon | Build ResultsPage.jsx | Full results dashboard: RecommendationCard + ComparisonTable + FeatureImportance + OverfitIndicator | ML components | All ML results displayed correctly |
| Mon | Build RecommendationCard component | Highlighted best-model card with justification text, download button, SHAP link | Card component | Recommendation renders with real data |
| Tue | Build ComparisonTable component | Multi-model table with sort-by-metric, highlight best, colored performance bars | DataTable variant | All models compared side-by-side |
| Tue | Build FeatureImportance + OverfitIndicator | Horizontal bar chart (Recharts), train-test gap visual indicator | Recharts | Charts render with correct data |
| Wed | Build ChatContainer + ChatMessage | Full chat layout: scrollable message list, user/assistant bubbles, citation cards inline | UI components | Chat appearance matches wireframe |
| Wed | Build ChatInput + ProviderSelector | Text input with send, LLM provider dropdown, suggested question chips | Dropdown, Button | Input works; provider switchable |
| Thu | Build ChatPage.jsx | Full chat page: ChatContainer + sidebar with dataset stats | Chat components | Chat page is functional (with mock data if API not ready) |
| Thu | Integrate chat with API | Connect to POST /chat/message, display response with citations, handle loading/error | Chat API (P3) | Real LLM responses shown with citations |
| Fri | Build ReportPage.jsx | Report config (section checkboxes, format selector, title input) + preview panel + download buttons | Report components | Reports generate and display correctly |
| Fri | Build DashboardPage.jsx | User dashboard: dataset list, job history, quick actions | All previous | Dashboard shows all user data |

### 🟡 P3 — API & Integration Engineer

| Day | Task | Deliverables | Depends On | Done When |
| --- | --- | --- | --- | --- |
| Mon | Build LLM provider abstraction | llm/base.py, openai_provider.py, anthropic_provider.py, google_provider.py, factory.py | API keys configured | All 3 providers callable through factory |
| Mon | Build LLM fallback chain | factory.py — retry with backoff, fallback to next provider on failure | Provider implementations | Fallback activates on provider error |
| Tue | Build chat schemas | schemas/chat.py — ChatMessageRequest, ChatResponse, Citation, ChatSettings | Coordinate with P1 | Schemas match RAG service output |
| Tue | Build chat router | routers/chat.py — POST /chat/message, GET /chat/history/{conversation_id}, PUT /chat/settings | RAGService (P1), LLM providers | Chat endpoint returns grounded answers |
| Wed | Build report schemas | schemas/report.py — ReportRequest, ReportResponse, section list | Coordinate with P1 | Schemas match report service output |
| Wed | Build report router | routers/report.py — POST /report/generate, GET /report/{id}, GET /report/download/{id} | ReportService (P1) | Reports generate async; downloadable |
| Thu | Build SHAP/explainability endpoints | Add GET /ml/shap/{dataset_id} — return SHAP plot URLs; GET /ml/model-card/{dataset_id} | Explainability (P1) | SHAP plots and model cards accessible via API |
| Thu | PII detection middleware | Middleware to scan uploaded data for PII patterns (email, phone, SSN); warn user, don’t block | Ingestion pipeline | PII warnings returned in upload response |
| Fri | End-to-end test: upload → clean → train → chat → report | Full flow through API; verify all pieces connect | All endpoints | Complete flow documented with screenshots |
| Fri | API rate limiting (per user) | Add rate limit headers; track via Redis; return 429 with Retry-After header | Redis, all routers | Rate limits enforced per endpoint group |

### 🟠 P4 — DevOps Engineer

| Day | Task | Deliverables | Depends On | Done When |
| --- | --- | --- | --- | --- |
| Mon | Add sentence-transformers + FAISS to backend image | Update requirements.txt + Dockerfile; ensure model downloads cached in Docker layer | P1 requirements | Backend image builds with ML dependencies |
| Tue | Set up model caching in Docker | Download all-MiniLM-L6-v2 during Docker build; mount as volume | sentence-transformers | Model loads from cache, not downloaded at runtime |
| Wed | Configure Celery queue separation | Separate ML queue (2 workers) from data/report queue (4 workers) in docker-compose | Celery tasks | Workers consume from correct queues |
| Thu | Set up staging deployment | Deploy to cloud VM or VPS: docker compose up with production config, SSL via Let’s Encrypt | Deploy script | Staging accessible via HTTPS |
| Fri | Monitoring: add Prometheus + Grafana (basic) | docker-compose.monitoring.yml — Prometheus scrapes FastAPI metrics; Grafana dashboard | Docker stack | Basic dashboard: request rate, latency, error rate |

### 🟣 P5 — QA & Documentation Engineer

| Day | Task | Deliverables | Depends On | Done When |
| --- | --- | --- | --- | --- |
| Mon | Write unit tests: RAG service | test_rag_service.py — chunk generation, retrieval quality gate, prompt construction, grounding validation | RAGService (P1) | ≥10 test cases |
| Tue | Write unit tests: LLM providers | test_llm_providers.py — factory creation, fallback chain, error handling (mocked APIs) | LLM providers (P3) | ≥8 test cases |
| Wed | Write integration test: chat flow | test_chat_flow.py — upload → index → ask question → verify citations | Chat API (P3) | Full chat flow passes |
| Thu | Write ML validation tests | test_classification.py (Iris ≥95% acc), test_regression.py (R² ≥0.80), test_clustering.py (silhouette ≥0.70) | ML pipeline (P1) | Baselines met on standard datasets |
| Fri | Manual QA: full flow with 5 different datasets | Test with: clean CSV, messy Excel, imbalanced data, high-cardinality, small dataset | Full system | Bug list with severity; UX feedback notes |

## Week 4: Polish & Ship (Mar 17 — Mar 21)

Goal: Fix all P0 bugs, integration testing, performance tuning, final documentation, and MVP demo.

### 🔵 P1 — Backend Engineer

| Day | Task |
| --- | --- |
| Mon | Fix all P0 bugs from QA reports; handle edge cases discovered in testing |
| Tue | Performance tuning: optimize slow queries, reduce memory usage in cleaning pipeline, add streaming for large files |
| Wed | Add error recovery: graceful handling of OOM, timeout, corrupted files; meaningful error messages |
| Thu | Code review all backend code; refactor any tech debt; add docstrings to all public functions |
| Fri | Support demo preparation; fix any last-minute issues; tag v0.1.0 release |

### 🟢 P2 — Frontend Engineer

| Day | Task |
| --- | --- |
| Mon | Fix all UI bugs; polish responsive design; dark theme verification |
| Tue | Add empty states, error boundaries, and loading skeletons to all pages |
| Wed | Accessibility audit: keyboard navigation, screen reader, color contrast; fix issues |
| Thu | Performance: lazy-load pages (React.lazy), optimize bundle size, add page transitions |
| Fri | Final visual polish; demo preparation; record walkthrough video |

### 🟡 P3 — API & Integration Engineer

| Day | Task |
| --- | --- |
| Mon | Fix all API bugs; verify all error codes and messages are correct |
| Tue | Add request validation edge cases: empty files, invalid JSON, oversized payloads |
| Wed | Write API usage guide: curl examples for every endpoint; add to documentation |
| Thu | Security review: verify auth on all endpoints, check for unprotected routes, sanitize inputs |
| Fri | Swagger docs final review; support demo; tag v0.1.0 |

### 🟠 P4 — DevOps Engineer

| Day | Task |
| --- | --- |
| Mon | Production Docker compose: no dev overrides, secrets via env, restart policies |
| Tue | Load test: Locust with 50 concurrent users; identify and fix bottlenecks |
| Wed | Set up production deployment (cloud): SSL, domain, DNS, auto-restart |
| Thu | Configure alerts: error rate, latency, disk space; Slack notification integration |
| Fri | Final deployment; smoke test; support demo |

### 🟣 P5 — QA & Documentation Engineer

| Day | Task |
| --- | --- |
| Mon | Regression testing: re-run all test suites after bug fixes; verify coverage ≥70% |
| Tue | Write user-facing README.md: badges, features, screenshots, quickstart, contributing |
| Wed | Update all DOCS/ files to match actual implementation; fix any discrepancies |
| Thu | Write CHANGELOG.md for v0.1.0; create release notes |
| Fri | Final manual QA pass; prepare demo script; support demo |

## Communication & Coordination

### Daily Standup (15 min, 10:00 AM)

Each person answers: 1. What I completed yesterday 2. What I’m working on today 3. Any blockers

### Coordination Points

| When | Who | What |
| --- | --- | --- |
| Mon W1 | All | Kick-off: align on architecture, schemas, conventions |
| Fri W1 | All | Demo: each person shows working piece; integration check |
| Wed W2 | P1 + P3 | API contract review: verify schemas match implementations |
| Wed W2 | P2 + P3 | Frontend integration session: verify API shapes match components |
| Fri W2 | All | Demo: upload → clean → train → results (end-to-end) |
| Fri W3 | All | Demo: full flow including chat + reports |
| Wed W4 | All | Code freeze: no new features; bug fixes only |
| Fri W4 | All | MVP demo + retrospective |

### Git Workflow

main ──────────────────────────────────────────────────── (production)
  │
  └── develop ─────────────────────────────────────────── (integration)
        │
        ├── feature/p1-data-pipeline ──── (P1 branches)
        ├── feature/p2-upload-page ────── (P2 branches)
        ├── feature/p3-ml-router ──────── (P3 branches)
        ├── feature/p4-docker-setup ───── (P4 branches)
        └── feature/p5-unit-tests ─────── (P5 branches)

- Branch naming: feature/{person}-{short-description}

- PR required: All merges to develop require 1 review

- CI must pass before merge

- develop → main only on Friday demos (after QA sign-off)

## Risk Mitigation

| Risk | Probability | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- |
| LLM API keys not provisioned | Low | Blocks chatbot (Week 3) | Provision keys in Week 1; test connectivity | P3 |
| FLAML training exceeds memory | Medium | Breaks ML pipeline | time_budget=300, memory monitoring, smaller model pool | P1 |
| Frontend-backend schema mismatch | Medium | Integration delays | Joint schema review Wed W2; TypeScript-like Zod schemas on frontend | P2 + P3 |
| CI pipeline flaky | Medium | Blocks merges | Fix flakes immediately; use pytest-rerunfailures | P4 |
| Scope creep | High | Delays MVP | Strict feature freeze; anything not in plan goes to backlog | All |
| Team member unavailable | Low | Delays their track | Cross-training in Week 1; documented handoff procedures | All |

## MVP Definition of Done

### Must-Have for v0.1.0 Release

- User can register and log in

- User can upload CSV/XLSX files (≤200MB)

- System auto-detects column types with ≥95% accuracy

- Data cleaning pipeline handles nulls, outliers, duplicates

- Before/after data quality comparison shown

- Task type (classification/regression) auto-detected

- ≥5 ML models trained via FLAML

- Best model recommended with justification and feature importance

- RAG chatbot answers questions with citations using GPT-4

- Chatbot says “I don’t know” instead of hallucinating

- Basic HTML report generated with data quality + model results

- All pages responsive (mobile, tablet, desktop)

- Docker Compose runs full stack with single command

- CI pipeline passes: lint + tests + build

- ≥70% backend test coverage

- README with setup instructions

### Nice-to-Have (if time permits)

- Claude + Gemini support (multi-LLM)

- PDF report export

- SHAP plots in dashboard

- Dark theme

- Clustering support